Project Summary for EPUAP website

Project Title:

EPUESP: Development and Pilot Validation of a Standardized European Platform for Pressure Ulcer Epidemiology Across Care Settings

Project Team:

- Principal Investigator: Alexandre Marques Rodrigues (University of Aveiro, Portugal)

- Pedro Sardo (University of Aveiro, Portugal)

- Biagio Nicolosi (Meyer Children’s Hospital IRCCS, Italy)

- Francisco Hernandez-Martinez (University of Las Palmas de Gran Canaria, Spain)

Project Focus:

Development and pilot validation of a standardized, scalable European platform for the epidemiological surveillance of pressure injuries across hospital, community, and long-term care settings.

Introduction:
Pressure injuries represent a significant public health challenge across Europe, contributing to increased morbidity, mortality, healthcare costs, and reduced quality of life. Despite their clinical relevance, current epidemiological data are fragmented and lack standardization, limiting comparability across countries and care settings. Existing studies often use heterogeneous methodologies, hindering benchmarking and coordinated European strategies. This project addresses this gap by proposing a harmonized methodological framework to structure on future an European data aggregation platform.

Project Aims:

The primary aim is to develop and pilot-test a standardized framework for pressure injury prevalence assessment across European care settings.

Secondary aims include:

- Assessing the feasibility and applicability of a standardized protocol across countries and settings

- Estimating point prevalence of pressure injuries in hospital, community, and long-term care

- Evaluating inter-rater agreement among trained assessors

- Defining functional and technical requirements for a future European epidemiological platform

Key Milestones:

- Protocol finalization and harmonization (Months 1–3)

- Development of data collection tools and ethicas aproval process (Months 3–7)

- Training of assessors across participating countries (Months 7–9)

- Data collection (Portugal, Spain, Italy) (Months 9–15)

- Data integration and statistical analysis (central database) (Months 14–17)

- Refinement of platform structure and methodological framework (Months 17–20)

- Dissemination of results (Months 20–24)

References:

- Isfahani, P., et al. (2024). Prevalence of hospital-acquired pressure injuries in ICUs. Patient Safety in Surgery.

- Moore, Z. E., et al. (2019). Pressure ulcer prevalence in Europe. Journal of Wound Care.

- Sardo, P. M. G., et al. (2023). Pressure ulcer prevalence and incidence. Journal of Tissue Viability.

- Rodrigues, A., et al. (2016). Informal caregiving and pressure ulcers. Journal of Clinical Nursing.

- Silva, A., et al. (2013). Economic cost of pressure ulcers. Revista da Escola de Enfermagem da USP.

- Rodrigues, A., et al. (2014). Pressure ulcer prevalence in the Azores.

- Triantafyllou, C., et al. (2021). Epidemiology of pressure ulcers in Europe. International Journal of Nursing Studies.

- Vanderwee, K., et al. (2007). European pressure ulcer prevalence pilot study. Journal of Evaluation in Clinical Practice.